## Contents
Department of Health annual report 2022-23 – machine readable dataset:
Capital projects reaching practical and financial completion
Contents
Capital projects reaching practical completion during the financial year ended 30 June 2023
Capital projects reaching financial completion during the financial year ended 30 June 2023
Accessibility
To receive this data in another format, email corporate reporting
<corporate.reporting@health.vic.gov.au>.
Copyright
With the exception of any images, photographs or branding (including, but not limited to the Victorian Coat of Arms, the Victorian Government logo or the Department of Health logo), this work, Department of Health Annual Report 2022–23, is licensed under a Creative Commons Attribution 4.0 licence.
The terms and conditions of this licence, including disclaimer of warranties and limitation of liability are available at Creative Commons Attribution 4.0 International <https://creativecommons.org/licenses/by/4.0/legalcode>.
You are free to reuse the work under that licence, on the condition that you credit the State of Victoria, Australia (Department of Health) as the author and/or owner of the work, indicate if any changes have been made to the work and comply with the other licence terms.
In this document, ‘Aboriginal’ refers to both Aboriginal and Torres Strait Islander people. ‘Indigenous’ or ’Koori/Koorie’ is retained when part of the title of a report, program or quotation.
ISSN 2653-1852 (online) (DH 2304411)
Available at Department of Health annual report <https://www.health.vic.gov.au/department-of-health-annual-report>

## Capital projects prac. compl.
Capital projects reaching practical completion during the financial year ended 30 June 2023
Project name | Original completion date | Latest approved completion date | Practical completion date | Reason for variance in completion dates | Original approved TEI(a) budget ($M) | Latest approved TEI budget ($M) | Actual TEI cost ($M) | Variation between actual cost and latest approved TEI budget ($M) | Reason for variance from latest approved TEI budget
Echuca Wellness Centre (Echuca) | 2022-12-01 | 2022-12-01 | 2022-09-01 |  | 8.3 | 8.3 | 7.969 | 0.331 | Balance of funding is required for financial closeout of the project, expected in the next financial year.
Goulburn Valley Health redevelopment – planning and development (Shepparton) | 2021-06-01 | 2023-12-01 | 2023-06-01 |  | 169.525 | 229.349 | 221.021 | 8.328 | Balance of funding is required for financial closeout of the project, expected in the next financial year.
Statewide Child and Family Mental Health Intensive Treatment Centre (statewide) | 2020-06-01 | 2022-12-01 | 2023-05-01 |  | 7.3 | 7.3 | 7.3 | 0 | N/A
Victorian Heart Hospital (Clayton) | 2022-06-01 | 2023-12-01 | 2022-12-01 |  | 15 | 577 | 522.143 | 54.857 | Balance of funding is required for financial closeout of the project, expected in the next financial year.
Wantirna aged care redevelopment (Wantirna) | 2023-06-01 | 2023-06-01 | 2022-08-01 |  | 81.58 | 81.58 | 75.939 | 5.641 | Balance of funding is required for financial closeout of the project, expected in the next financial year.
Women’s Prevention and Recovery Care (PARC) Service (metropolitan various) | 2020-06-01 | 2023-06-01 | 2022-09-01 |  | 8.4 | 8.4 | 8.308 | 0.092 | Balance of funding is required for financial closeout of the project, expected in the next financial year.
Wonthaggi Hospital emergency department expansion (Wonthaggi) | 2023-06-01 | 2023-06-01 | 2023-04-01 |  | 115 | 115 | 111.899 | 3.101 | Balance of funding is required for financial closeout of the project, expected in the next financial year.
(a) Total estimated investment

## Capital projects fin. compl.
Capital projects reaching financial completion during the financial year ended 30 June 2023
Project name | Practical completion date | Financial completion date | Original approved TEI (a) budget ($M) | Latest approved TEI budget ($M) | Actual TEI cost ($M) | Variation between actual cost and latest approved TEI budget ($M) | Reason for variance from latest approved TEI budget
Austin Hospital Central Sterile Services Department (Heidelberg) | 2023-06-01 | 2023-06-01 | 7.8 | 7.8 | 7.8 | 0 | N/A
Engineering infrastructure replacement program 2017–18 (statewide) | 2023-06-01 | 2023-06-01 | 25 | 25 | 25 | 0 | N/A
Engineering infrastructure replacement program 2018–19 (statewide) | 2023-06-01 | 2023-06-01 | 25 | 25 | 25 | 0 | N/A
Forensic mental health bed-based services expansion (Fairfield) | 2023-06-01 | 2023-06-01 | 40 | 31 | 31 | 0 | N/A
Health Service Violence Prevention Fund (statewide) | 2023-06-01 | 2023-06-01 | 20 | 20 | 20 | 0 | N/A
Medical equipment replacement program (statewide) | 2023-06-01 | 2023-06-01 | 70 | 70 | 70 | 0 | N/A
Mental health and alcohol and drug facilities renewal 2018–19 (statewide) | 2023-06-01 | 2023-06-01 | 10 | 10 | 10 | 0 | N/A
Sunshine Hospital Emergency Department (St Albans) | 2022-09-01 | 2022-09-01 | 29.6 | 28.431 | 28.431 | 0 | N/A
(a) Total estimated investment