## Contents
Department of Health 2023-24 Annual Report – machine readable dataset:
Capital projects completed
Contents
Capital projects reaching practical completion during the financial year ended 30 June 2024
Capital projects reaching financial completion during the financial year ended 30 June 2024
Accessibility
To receive this data in another format, email corporate reporting
<corporate.reporting@health.vic.gov.au>.
Copyright
With the exception of any images, photographs or branding (including, but not limited to the Victorian Coat of Arms, the Victorian Government logo or the Department of Health logo), this work, Department of Health annual report 2023-24, is licensed under a Creative Commons Attribution 4.0 licence.
The terms and conditions of this licence, including disclaimer of warranties and limitation of liability are available at Creative Commons Attribution 4.0 International <https://creativecommons.org/licenses/by/4.0/legalcode>.
You are free to reuse the work under that licence, on the condition that you credit the State of Victoria, Australia (Department of Health) as the author and/or owner of the work, indicate if any changes have been made to the work and comply with the other licence terms.
In this document, where the term ‘Aboriginal’ is used it refers to both Aboriginal and Torres Strait Islander people. Indigenous, First Peoples or Koori/Koorie is retained when it is part of the title of a report, program or quotation.
ISSN 2653-1852 (online)
Available at Department of Health annual report <https://www.health.vic.gov.au/department-of-health-annual-report>

## Capital projects prac. compl.
Capital projects reaching practical completion during the financial year ended 30 June 2024
Project name | Original completion date | Latest approved completion date | Practical completion date | Reason for variance in completion dates | Original approved Total Estimated Investment (TEI) Budget ($M) | Latest approved TEI budget ($M) | Actual TEI cost ($M) | Variation between actual cost and latest approved TEI budget ($M) | Reason for variance from latest approved TEI budget
A pathway to more acute mental health beds (Statewide) | Jun. 2022 | Mar. 2025 | Dec. 2023 | Project achieved practical completion ahead of schedule | 492.2 | 492.2 | 474.219 | 17.981 | Balance of funding is required for financial closeout of the project, expected in the next financial year.
Alcohol and other drugs residential rehabilitation treatment expansion (St Albans) | Jun. 2023 | Mar. 2024 | Dec. 2023 | Project achieved practical completion ahead of schedule | 9.42 | 10.296 | 9.399 | 0.897 | Balance of funding is required for financial closeout of the project, expected in the next financial year.
Building a bigger and better Latrobe Hospital (Traralgon) | Jun. 2020 | Jun. 2024 | Dec. 2023 | Project achieved practical completion ahead of schedule | 7 | 223.5 | 212.209 | 11.291 | Balance of funding is required for financial closeout of the project, expected in the next financial year.
Engineering infrastructure and medical equipment replacement program 2019–20 (statewide) | Jun. 2020 | Jun. 2024 | Jun. 2024 | NA | 60 | 60 | 56.525 | 3.475 | Balance of funding is required for financial closeout of the project, expected in the next financial year.
Reforming Clinical Mental Health Services (Melbourne) | Jun. 2023 | Jun. 2023 | Aug. 2023 | Four of the five funded sites were completed on time. The final site at the Royal Melbourne Hospital was delayed due to latent conditions | 48.1 | 34.741 | 33.772 | 0.969 | Balance of funding is required for financial closeout of the project, expected in the next financial year.
Relocation of Barwon Health Facilities (Geelong) | Jun. 2024 | Jun. 2024 | Jul. 2023 | Project achieved practical completion ahead of schedule | 20 | 8.5 | 8.5 | 0 | N/A
Royal Victorian Eye and Ear Hospital Redevelopment (Melbourne) | Dec. 2017 | Jun.2024 | June. 2024 | NA | 165 | 319.807 | 317.323 | 2.484 | Balance of funding is required for financial closeout of the project, expected in the next financial year.

## Capital projects fin. compl.
Capital projects reaching financial completion during the financial year ended 30 June 2024
Project name | Practical completion date | Financial completion date | Original approved Total Estimated Investment (TEI) budget ($M) | Latest approved TEI budget ($M) | Actual TEI cost ($M) | Variation between actual cost and latest approved TEI budget ($M) | Reason for variance from latest approved TEI budget
Echuca Wellness Centre (Echuca) | Sept. 2022 | Jun. 2024 | 8.3 | 8.3 | 7.984 | 0.316 | Project completed under budget
Goulburn Valley Health redevelopment – planning and development (Shepparton) | Jun. 2023 | Jun. 2024 | 169.525 | 229.349 | 229.349 | 0
Northern Hospital inpatient expansion – Stage 2 (Epping) | Aug. 2021 | Jun. 2024 | 162.672 | 162.672 | 161.254 | 1.418 | Project completed under budget
Relocation of Barwon Health clinical facilities (Geelong) | Jul. 2023 | Jun. 2024 | 20 | 8.5 | 8.5 | 0
Statewide Child and Family Mental Health Intensive Treatment Centre (statewide) | May. 2023 | Jun. 2024 | 7.3 | 7.3 | 7.3 | 0
The New Footscray Hospital – planning and critical infrastructure (Footscray) | Sept. 2022 | Jun. 2024 | 15 | 15 | 12.864 | 2.316 | Project completed under budget
Wantirna aged care redevelopment (Wantirna) | Aug. 2022 | Jun. 2024 | 81.58 | 76.58 | 75.926 | 0.654 | Project completed under budget
Women’s Prevention and Recovery Care (PARC) Service (metropolitan various) | Sept. 2022 | Jun. 2024 | 8.4 | 8.4 | 8.397 | 0.003 | Project completed under budget
Youth Prevention and Recovery Care Service (metropolitan) | Dec. 2021 | Jun. 2024 | 11.9 | 12.9 | 12.808 | 0.092 | Project completed under budget